## QA_Registry
LAPR4 - Client
Questions and Answers Forum registry table
|  |  |  | US/UC | Conceitos
ID | DATE OF QUESTION | QUESTION | ANSWER | NFR01 | USER | Managers / Administrators | Teachers | Students | Course | Class | Meetings | Exams | Boards | _ | _ | General application info
1 | Tuesday, 14 de March de 2023 às 15:50 | Project User Looking at the users, they are to be given a short name and a full name. Should the short name be part of the full name? | Usually my suggestion for this type of doubts is to search for the most common approach to solve the issue. I would say that it is part of the analysis of the problem. After that, you should take a decision and justify that decision. Having said that, as a client, I should say that my interpretation of short name is like a given name. |  | DONE | [11 empty] | x
2 | Tuesday, 14 de March de 2023 às 15:51 | Project course As for the course, there are 2 things bothering me: - The unique code is said to be input and the identifier is automated. Should they be different things, or was there any confusion? - It is mentioned a title for the course and a unique name. Are they the same? | Yes, I think the specification has some contradictory or confusing statements regarding courses. I should say that maybe the ideia is that a course: - has unique code inputed by the administrator, e.g., "JAVA-1, that is used to identify it - it has a name (name and title may refer to the same property of courses, and I would say that there is no need for it to be unique) |  |  | DONE |  |  | DONE
3 | Tuesday, 14 de March de 2023 às 15:52 | Project - Exame As for the exam, is the title written in the exam the same as its unique title to identify? They are both mentioned, but in different parts of the project. | Page 14: "It has a unique title and a small description.". Therefore my answer should be that the title is unique. Maybe it could be used to identify the exam. It is also mentioned that the contents and structure of exams is to be based on the Moodle platform (particularly for the questions). As such, maybe a study of that platform is a good starting point for understanding how this feature of the eCourse project should/can "work". | [8 empty] | DONE
4 | Tuesday, 14 de March de 2023 às 15:53 | Project - UI Is the UI supposed to be ran on the console or should there be an elaborate UI to be developed? | There are some non-functional requirements relating to that questions. My answer should be that I expect a solution in accordance with the program of the courses of LEI up until this semester (including this semester). Therefore, in general, what is expected is a Java Console Application (or set of applications). But there are some exceptions, as presented in the non-functional requirements. | [12 empty] | DONE
5 | Wednesday, 15 de March de 2023 às 16:18 | UI from the project Me and my group had some doubts about how the application (s) were supposed to work. So we came up with 3 different ideas. 1. Initially it is asked the role to be analyzed. Then, an application would run for the role chosen. So there would be an application for each role 2. The login would be asked within the application, and then it would show the information possible to show within the role of the logged user 3. There would be different applications to be ran right from the start and only the people with the role of each application could log in into that We would love to know if any of these ideas are correct or if there is other way we may be missing. | According to the diagram on page 11, it is clear that the goal is to have a solution with several "parts". Some of these parts are identified as "apps" (from an end user point of view). These apps have specific user roles. From the Aliens perspective, the way you may achieve "that" is not particularly relevant. However, the Client may have the intention to deploy each app/part of the solution into different machines. | [12 empty] | DONE
6 | Thursday, 16 de March de 2023 às 20:40 | User Roles and Question Types Do the system has to support an option to create new user roles that are not specified at the system specification documents or the system will always have just the three user roles described? The same question can be applied to the question types (e.g., Multiple Choice and Short Answer). Should the system support the creation of new question types? | Regarding user roles, the solution should support the ones necessary to cover all the actual functional requirements. Regarding question types, only the referenced in the specification are required. |  | DONE | [6 empty] | DONE
7 | Friday, 17 de March de 2023 às 15:13 | Number of Students in a Course As it is said in the project description, "Courses may have a minimum and a maximum number of enrolled students. This may limit the possibility of opening (i.e. starting) courses that do not satisfy the limits.", that being showed we want to know if it is optional to have limits on the course? If its mandatory to have the limits, who can establish limits of students to the course?, what are the acceptable limits of students in a course? And what are the conditions for a course to have limits? | Managers should be able to specify the limits. In my opinion the system should notify the manager if a course is out of the enrolment limits (before this course is changed to "in progress"). But, in the end, it is up to the manager to follow/enforce or not, the limits. |  |  | DONE |  |  | DONE
8 | Friday, 17 de March de 2023 às 18:38 | Students in different courses Can one student be enrolled in different courses? | Yes. I see no reason not to (section 5.1.3: "Students enroll in courses."). |  |  |  |  | DONE | DONE
9 | Sunday, 19 de March de 2023 às 14:48 | Shared Boards - Permissions when sharing a board when a user shares a board with multiples users are the permissions (read or write) defined per user ? Or are they the same for every user it is shared with ? | The owner of the board should be able to specify the access that each user has to the board (read or write). |  | DONE | [7 empty] | DONE
10 | Monday, 20 de March de 2023 às 09:55 | Cliente | É só para informar que não é obrigatório usar o inglês nas vossas questões (mas podem continuar a faze-lo). | [12 empty] | DONE
11 | Monday, 20 de March de 2023 às 20:57 | Course Edition specification regarding the edition of a course to be taken, are there any attributes to specify it? (such as year and/or semester, for example)(practical example: ESOFT 2023 2nd semester) | "A course is simply a course". There is no hierarchy or containment relation with other concept, such as program or semester. From the specification: "Different editions of a course are to be considered different courses (e.g., Intro-Math-Sem01, Intro-Math-Sem02)". | [5 empty] | DONE
12 | Tuesday, 21 de March de 2023 às 20:56 | Re: Course Edition specification I still have a doubt, if the course name and edition are the same but the unique code is different, is it to be considered a different course or is it the same as the one already in the system? | A course has a "unique code inputed by the administrator, e.g., 'JAVA-1'.". It is this unique code that identifies the course. According to the specification there are no specific constraints regarding the title of the course. | [5 empty] | DONE
13 | Monday, 20 de March de 2023 às 21:10 | Student/Teacher tax payer number what should the tax payer number verifications be? Of course it is unique, but what format does it follow, since it varies from country to country? | For the project with should focus on supporting the Portuguese tax payer number. You may consider single person tax payer (no need to support companies). |  |  |  | DONE | DONE
14 | Monday, 20 de March de 2023 às 21:20 | Course state In the document you provided it says "A course may be open or closed." but I saw a post of yours where you mentioned "(before this course is changed to "in progress")". So does that mean it can be open (to enroll), closed(after it ends) and in progress(decurring, closed for enrollment)? | Yes, a course may have several states. Section "5.2.1 Course" exemplifies the usual cycle of a course. | [5 empty] | DONE
15 | Tuesday, 21 de March de 2023 às 13:26 | Questions for an Exam Can the same question be used in different exams? Or are the questions made for a specific exam? | At the present moment, when designing the exam, the user specifies all its structure (including the questions, as described in section 5.2.4). There is no "database" of questions. NOTE: However, it is possible that new user stories regarding exams will be added (in sprint B and C) for teams/groups with an extended number of students enrolled in LPROG. |  | DONE | [6 empty] | DONE
16 | Tuesday, 21 de March de 2023 às 13:47 | System User multi-role should the user be multi-role? For example, can a system user be a teacher and a student or a manager at the same time? | I see no need for that. For me, each user as only one specific role in the system. |  | DONE
17 | Tuesday, 21 de March de 2023 às 14:18 | Meetings Boa tarde nos estamos a ter uma duvida sobre qual e a diferença entre meetings e classes | Os conceitos são bastante próximos mas existem diferenças. Por exemplo, as aulas são regulares e têm participantes pré-definidos. As reuniões são definidas por qualquer utilizador, têm o conceito de convite, podem-se especificar os participantes, etc. Ou seja, existem ainda diferenças significativas. | [6 empty] | DONE | DONE
18 | Tuesday, 21 de March de 2023 às 16:06 | Overlapping meetings and classes Can a meeting and class overlap? If so, should the system notify that there is an overlap and for which user(s)? | Regarding classes: FRC09 - Schedule of Class A teacher schedule a class (always a recurring class, happens every week). System must check if the Teacher is available for the class period Regarding Meetings: FRM01 - Schedule a Meeting A user schedules a meeting. The system must check if all participants are available and send invitations to participants. In the case of Meetings they should not be created if the participants are not available (i.e., they may have classes or other meetings at the same time). | [6 empty] | DONE | DONE
19 | Tuesday, 21 de March de 2023 às 16:10 | Format rules for teacher acronym Is there any format rule regarding the acronym for the teacher length-wise or which characters should or should not be used? Also, should this acronym be unique for each teacher? | I think a sequence of capitalised words should be used for the teacher acronym. Maybe the length could be a configuration setting of the application. I think it would be wise to enforce that acronyms be unique. |  |  |  | DONE
20 | Tuesday, 21 de March de 2023 às 17:21 | Feedback of an exam In regards to the exam, what do you mean by feedback and grading? Is it necessary to save the answers of the users showing and comparing them with the correct answer? Furthermore is it necessary to save the answer of the question? | The ideia is to have feedback and grading similarly to what is available for tests in the moodle platform. How you may achieve this is not up to me to decide. | [8 empty] | DONE
21 | Tuesday, 21 de March de 2023 às 17:47 | Schedule availabe before or after enrollment or irrelevant? Should a class be already scheduled, recurring or not, for a course to be able to open for enrollments, or is this irrelevant? | ????? Ainda n respondeu ??????
22 | Tuesday, 21 de March de 2023 às 17:52 | Teacher can be in charge of several courses? It is mentioned that only one teacher can be in charge of a course, but can the same teacher be in charge of several other courses? | Yes, a teacher can be in charge of several courses. |  |  |  | DONE |  | DONE
23 | Tuesday, 21 de March de 2023 às 19:44 | Teacher with the role of Manager If the Teacher can also be a manager, can this teacher create or eliminate courses / manage students outside its disciplinary course? Or does the manager only operate in its disciplinary course, and there are a need for a minimal of one maneger per course? | Regarding the second question, I already answered a similar question regarding roles. Also, I do not see how teachers have anything to do with creation of courses or managing students. Please read carefully the specification document. |  |  |  | DONE
24 | Wednesday, 22 de March de 2023 às 14:03 | Board notification Where should a notification regarding the update of a board post appear? In the user app, the shared board app or both? | For me it should be in the Shared Board App. | [9 empty] | DONE
25 | Thursday, 23 de March de 2023 às 09:49 | Meeting Participants While trying to understand the concept of a meeting, a specific question came to me: - Can any user of the system invite any other user? For example, can a student invite another student who is in a different course, or can a manager can create a meeting with any group of teachers. | When in the document specification the term "User" is used it usually means "any user" of the system. Therefore, any user of the system can schedule a meeting and be a participant in a meeting. |  | DONE | [5 empty] | DONE
26 | Thursday, 23 de March de 2023 às 16:42 | Meetings - Response to them As I read the little information we had about meetings, I had some doubts on this functional requirement: FRM04 List Participants The system displays the lists of participants in a meeting and the response status (accept or reject meeting). When mentioning "accept or reject meeting", I though to myself about an invite being sent to the user and 2 options for the response: -The sent invite has already as a response "Rejected", so that it can either be changed to "Accepted" or stays as it is, seeing that if the user doesn't accept it, he will be rejecting it. -The sent invite has a response being "No answer" and, at a certain time near the begining of the meeting, the answer would change to "Rejected". The answer can be changed before it at any time to "Accepted" or "Rejected" I think that the 1st option would go more towards what you are looking for (by reading FRM04, it would only show the users who "accept or reject the meeting") but I wanna be sure. | Just a small note regarding meetings: their use cases have a priority (see excel file) level 5. This means that they usually only have to be developed by teams with 5 or more students (regarding essentially EAPLI and LAPR4). FRM01 relates to the fact that the system should check if participants are available before sending the invitations. For instance, checking if a user has no other class or meeting at the same time. The system should only invite participants with a free calendar at the time of the meeting. In FRM03, the user accepts or rejects an invitation. In FRM04, the status of someone that did not answer should be "no answer" or "unknown". To be noticed that there is "nothing" to do by the system at the time of the meeting. Nothing needs to "happen". The same applies for classes. | [7 empty] | DONE
27 | Friday, 24 de March de 2023 às 17:39 | Course e class Poderia esclarecer o que é um Course e o que é uma Class? | Um "course" é um curso. Mas será um curso de "curta duração", não confundir com um curso "de ensino superior", como uma licenciatura ou mestrado. Em inglês iríamos identificar isso como sendo um "program", que é constituído por vários "courses". Num curso de ensino superior, o mais similar a "course" seria uma unidade curricular ou disciplina. Uma "class" é uma aula (relativa a um "course"). | [5 empty] | DONE | DONE
28 | Saturday, 25 de March de 2023 às 09:55 | Listing users and other doubts I have some doubts about some requirements : 1) Is it necessary to know who created a specific exam? 2) Is it necessary to list exams that a specific teacher created? 3) Is it necessary to list exams that were taken by a specific student? 4) Is it necessary to know who created a specific user? 5) Is it necessary to know the manager that set a teacher to a specific course? 6) Is it necessary to know the manager that enrolled a student? | Regarding your questions, my generic answer is that you only have to implement the requirements that are specified in the document. "1) Is it necessary to know who created a specific exam?" I do not think there is any requirement that explicitly requires that. However, I can not answer if the technical solution of the problem may require that. "2) Is it necessary to list exams that a specific teacher created?" Once again, I do not see any requirement that specifies that. However, there is one very similar: FRE03-List Course Exams. "3) Is it necessary to list exams that were taken by a specific student?" FRE03 - List Grades should display the grades of a students. This regards previous exames taken by the student. "4) Is it necessary to know who created a specific user? 5) Is it necessary to know the manager that set a teacher to a specific course? 6) Is it necessary to know the manager that enrolled a student?" There is no requirement specific to all these questions. However, I do not know if the system must support "something" related to these questions. I think this is something related to the design of the solution, that you and your team must decide when designing the solution in order to meet the existing requirements. |  | DONE | DONE | DONE | DONE | DONE |  |  | DONE
29 | Saturday, 25 de March de 2023 às 16:10 | Meetings and classes I have a question about the meetings and classes. With the description of the functionalities/requirements of classes and meetings, wouldn't they be the same? Since both are online, in my point of view, it would make sense if a student could accept/reject a class as well, for example, and the same could be applied for the remaining requirements with the exception of creating classes. But of course, I might be missing something that totally nullifies this point of view. | There is no requirement that "says" the student can accept or reject a class. Only meetings have the possibility that participants may accept or reject the meeting. This does not apply to classes. | [6 empty] | DONE | DONE
30 | Saturday, 25 de March de 2023 às 16:48 | Board Line/Entry attributes As stated in the system specifications document, "Columns and rows may have titles. They may also be identified by an integer number from 1 to the maximum number", we wanted to clarify if it should be possible to have a column with no title and no identifier. Also, can the identifier of a column/row change once it's assigned? | In order for user to post content into a cell they must identify the cell. Therefore, I think at least, ir should be possible to identify the cell by the number of its column and the number of its row. If the cells have titles, these titles can be used to identify the cells. However, it should always be possible to identify a cell by the column number and row number. Regarding changing the title of the columns and rows after creating the board, there is nothing explicit about that. Therefore, I would accept the solution that does not support that possibility. | [9 empty] | DONE
31 | Sunday, 26 de March de 2023 às 19:19 | Manager role Does the Manager have the same attributes as Students and Teachers? (tay payer number, name) Is the name of each actor either the full name or the short name? | A manager should have only the attributes as described in section 5.1.1. Also in section 5.1.1: "All users should be identified in the system by their email.". It is also stated that "Each user should also provide its full name and short name". As mentioned before, the short name is like a given name, the short name someone chooses to be called. Therefore, all users should have a name (full name) and a short name. When later, the document refers that students and teachers should have names, please consider both full name and shot name (since both are users). |  |  | DONE | [10 empty] | X
32 | Monday, 27 de March de 2023 às 23:23 | Board Can a user own more than one board? | Yes. |  | DONE | [7 empty] | DONE
33 | Tuesday, 28 de March de 2023 às 14:12 | Exam Regarding the exam's section, our group had thought about 2 viable options in case of a missing student: -His grade would be considered a 0; -His grade would be considered N/A and a message/email would be sent to him regarding the missing exam If neither the options are the intended solution, it would be great to be provided with the best solution for you. | I think only FRE06 - List Course Grades is related to your question. I think that the system should not display the grade of a student that dit not take the exam, it should display, for instance, N/A. I also do not see any mention in the specification related to the notification of students when they miss an exam. |  |  |  |  | DONE | DONE |  |  | DONE
34 | Tuesday, 28 de March de 2023 às 14:37 | Exam Regarding the questions within the exam, should every type of question have a feedback? For example, a multiple choice question has 1 solution and 1 solution only. So, if the student's solution is right, he gets maximum grading on a question, and, if so, the feedback would be equal to the solution, for example: Solution : C Feedback: C -- 100% | The feedback is a text (regarding a question/answer) that may appear to the student when he/she finishes the exam. The teacher can use this text to "justify/explain" why the answer given by the student is wrong (if the student gave the a wrong answer) and what should be the right answer. But, basically, it is only "text". Every possible "wrong answer" may have a feedback. It may also be possible to specify the feedback for the right answer. Taken from the Moodle documentation "...If you wish, add general feedback. This is text that appears to the student after he/she has answered the question..." |  |  |  | DONE |  |  |  |  | DONE
35 | Tuesday, 28 de March de 2023 às 22:01 | shared board 1. uma célula pode ter mais do que um post it? 2. Se sim, é possível ter post-its de users diferentes na mesma célula? Se sim, até quantos? | 1. Neste momento (no âmbito deste projeto) isso não será necessário. A ser possível (uma célula com mais do que 1 post-it) isso iria dificultar algumas funcionalidades, como a que permite mudar um post-it. | [9 empty] | DONE
36 | Wednesday, 29 de March de 2023 às 11:38 | Exame Ao criar um exame, este pode ser marcado para mais do que um dia? | Relativamente a esta questão o que está na especificação é: "Exams have also an open and a close date. The open date is the time when students can start to take the exam. The close date is the deadline for students to submit the exam.". Portanto, eu diria que tem um "tempo" de abertura e um tempo de "fecho". O tempo de abertura tem de ser antes do tempo de fecho. Nada de especifico é dito sobre a duração do exame ou outro tipo de restrição, pelo que se devem aceitar exames que estão "abertos" por períodos que ultrapassam um dia. | [8 empty] | DONE
37 | Wednesday, 29 de March de 2023 às 12:12 | Acronyms We don't have any constraint to the teachers acronym on the system specifications documents. Will it be possible to have two differents with the same acronym? Will there be a maximum length to a taacher acronym? Are there any other details to be add to this topic? | Regarding this topic mu opinion is that the teacher acronym could be used to identify the teacher, therefore it should be unique. Following the example given, it seems the acronym should be formed by a sequence of capital letters. There is really no maximum number of characters, but I would provide the possibility of setting a maximum as a property configuration of the system (with a default value). Maybe this is a good rule for every similar case. |  |  |  | DONE
38 | Thursday, 30 de March de 2023 às 09:34 | FRE06 - List Course Grades In the Functional Requirement FRE06 it is said that "The system displays the grades of a class". However, how can a class have grades? You said before that, in our context, a class is a "aula" not a "turma". Did you mean course instead of class? | Yes, you are right, the requirement refers to the grades of the students of a course. In some contexts "class" can also be translated to "turma", or all the students in a "class". | [5 empty] | DONE | DONE
39 | Thursday, 30 de March de 2023 às 09:54 | Student taking an exam Is an exam available for all students of a certain course, or do the students of the course need to sign up to take an exam previously. | I think there is no "sign up" for exams. After the exam is created it should be available to all the students of that course, and all the students can/should take that exam. |  |  |  |  | DONE |  |  |  | DONE
40 | Thursday, 30 de March de 2023 às 10:31 | Board history In the requirements, it says that the system should maintain the history/log of all the updates on the board. There's someone specific that will be able to see those logs, or is it just something everyone that has access to the board can see? | The history in the boards is important for the following functional requirements: FRB06 - Undo Post-it Change A user undo the last change in a post-it FRB07 - View Board History A user views a history of updates in a board If a user as read access to the board he/she can view the history. |  | DONE | [7 empty] | DONE
41 | Thursday, 30 de March de 2023 às 21:56 | Board history Regarding the board history of FRB07, which information should be stored? For example: change date, change made, user? | I would say all the information that is needed for a possible "restore operation" in the future (so that it can be used again with "total" functionality). | [9 empty] | DONE
42 | Friday, 31 de March de 2023 às 14:19 | G004 -deployments Na US G004 gostaria de saber se temos que fazer deploy neste sprint e se tem alguma preferencia de onde o podemos alocar. | Algumas user stories deste sprint são relativamente vagas e dependem do vosso planeamento. Por exemplo, que aplicações (das previstas no capitulo 4 terão, de facto, já alguma "versão" para instalarem?). De qualquer das formas, a ideia é preparem o "deployment" em função dos objetivos de cada sprint. Do ponto de vista do cliente, seria interessante terem já uma versão "executável" (embora sem funcionalidades) das app Admin, Teacher e Student (e respectiva base de dados). Nota: Em concreto, e apenas para a UC de LAPR4, existem vários "níveis" de deployment, que estão identificados no critério de avaliação "Implantação/Deployment (10%)". | [12 empty] | DONE
43 | Friday, 31 de March de 2023 às 14:53 | Weekly classes duration Should we allow the users to choose until what date they want to schedule the weekly classes or should the weakly classes be scheduled until the end of the semester and if so what is the duration of the semester ? | Only teachers should be able to schedule classes. I think there is no requirement that refers to the course duration or the concept of term or semester. Therefore, if you do not consider the course to have a pre-established ending date, then you also should not consider the end of the recurrence (in fact, it will happen when the manager closes the course). If you consider that a course must have an ending date, then also consider the end of the recurrence of the classes to the same date. However, since "nothing" happens at the time of the classes, the option you take will have limited implications, I think, only at the validation of availability of participants. |  |  | DONE | DONE |  | DONE | DONE
44 | Friday, 31 de March de 2023 às 15:41 | Course creation When the Manager creates a Course, should there already be an assigned group of Teachers and Students associated with the created Course or should they be added later? | There are specific requirements for all these functionalities and they may take place after the course creation. For instance, FRC04, refers to setting the teachers of the course and FRC06 refers to the bulk enrolment of students. They both can take place after the creation of the course. However, I think there is no "problem" if the system supports that the manager do all these settings just "after" creating the course. |  |  | DONE |  |  | DONE
45 | Saturday, 1 de April de 2023 às 00:28 | Weekly classes recurrence Regarding weekly classes recurrence, should be considered as a recurrence class if it happens more than one day per week? For example, the same class can occur on mondays and wednesdays? | A class should be considered only one class ("aula"). This one class is always a recurring class. If a course has more than one class each week, then each class will be a recurring class. | [6 empty] | DONE
46 | Monday, 3 de April de 2023 às 00:03 | FRE06 - List Course Grades However, I have a further question, that I wrote in my previous 'post': "If so, how are courses evaluated? Is it an average between all taken exams?" Is this a typo? Meaning that classes are not evaluated, but courses instead. If so, how are courses evaluated? Is it an average between all taken exams? | The grades in FRE05 and FRE06 are related to the exams of the course. There is no need to do any calculation. The system, should display the grades of each exam that the student did take (FRE05) or display the grades for every exam of the course and for every student (in the case of FRE06). | [5 empty] | DONE |  |  | DONE
47 | Monday, 3 de April de 2023 às 13:16 | Manager Is it necessary to track changes that a manager has made? For example, it is necessary to know which manager created which course? | I think that what you suggest is a good practice. However, I think there is no explicitly requirement for that, for the role of manager. There are other roles and requirements that need that (for instance, users and boards or users and meetings). |  |  | DONE |  |  |  |  | DONE |  | DONE |  |  |  | X
48 | Monday, 3 de April de 2023 às 15:38 | Exams Good afternoon client, I have a question about the exams. After the exam being created, the teacher can still change it? If yes, can two (or more) teachers edit the same exam? | There is no explicit statement regarding editing an exam. However, there are several data to be specified for an exam and its specification can be complex. Therefore, as a Client of the system, I think that FRE01, in the perspective of a use case, can be a very long use case, including several steps, with, for instance, a step to validate the exam specification (according to the grammar). All these specifications and steps are prone to user errors. Therefore, maybe you should consider a final "publish" action to mark the end of the creation process or some other alternative solution to support this lengthy process. |  |  |  | DONE |  |  |  |  | DONE
49 | Saturday, 8 de April de 2023 às 16:06 | Teacher in charge and normal class teacher responsibilities In the document we can read: "Teachers are responsible for scheduling classes for their courses" and also "Each course must have a teacher in charge". Our question is: Can any teacher schedule classes for the courses he/she is in or only the teacher in charge can schedule classes for the course he/she is in charge? If only the teacher in charge for that course can schedule classes does that also mean that only he/she can schedule extra classes? The functional requirement FRC11 (Update Schedule of Class) is also related to the same responsibility doubt between the two roles. In the document we can also read: "Teachers can create exams." which made us question the same responsibility problem. Finally, could you clarify what responsibilities the teacher in charge has that a normal course teacher hasn't, in the system? And also, if you find it relevant, give some practical examples of what the teacher in charge will do in the system | For the requirements of the system you may consider that the roles of teacher and teacher in charge have the same capabilities. The only rule is that each course must have one teacher in charge. So, the system must register the teacher in charge for each course. The teacher in charge has more responsibilities than a regular teacher but, for the moment, they are outside the system to be developed (for instance, the program and contents of the course are a responsibility of the teacher in charge). |  |  |  | DONE |  |  | DONE |  | DONE
50 | Saturday, 15 de April de 2023 às 10:38 | Class duration We have a question about a class scheduling. When a teacher wants to schedule a class, do they introduce start date/time and end date/time, or start date/time and duration of the class? And in general, how often will the client want to consult the duration of the classes? | For the class the teacher should entre the start date/time and duration (see Section 5.1.2). The duration of the class is important when scheduling "events" (such a classes and meetings) because the system must comply with some scheduling rules, for instance, to avoid scheduling classes that are coincident with other classes of the same course (see Section 5.1.2). |  |  |  | DONE |  |  | DONE
51 | Tuesday, 18 de April de 2023 às 14:06 | G1006: List courses Relative to this US, "As User, I want to list all the courses that are available to me" what should we list according to the User role? Student: Courses that Student is enrolled Teacher: Courses that Teacher teaches Manager: All Courses Are these assumptions right? | Regarding Teachers and Managers I agree with you. Regarding students I think it is best to list all the courses in which the student is enrolled or may be enrolled (the enrolments are opened). If not, how would a student know the courses in which he/she can enrol? |  | DONE | DONE | DONE | DONE | DONE
52 | Tuesday, 18 de April de 2023 às 15:04 | US1009 - As Manager, I want to approve or reject students applications to courses We would like to know what are the requirements for a student to be accepted or rejected from an application to a course. | I think that decision can not be automatically taken by the system, it is a decision of the manager. The responsibility is of the manager according to course rules that ar out of the scope of this implementation. I think the system should only register the reason for the decision. |  |  | DONE |  |  | DONE
53 | Tuesday, 18 de April de 2023 às 18:07 | Students csv file Will we have a csv file example for the students data? | No, the client did not prepare any csv example. CSV is a standard file format. You should support the bulk enrolment of students in a course by have their identification in a csv file. |  |  |  |  | DONE
54 | Thursday, 20 de April de 2023 às 11:40 | US1010 e US1011- Schedule Class and ExtraClass Nestas duas US, pretende que seja mostrada a lista de Class/ExtraClass que já estão agendadas para que o professor saiba onde pode agendar? | Em termos de requisitos é importante que o sistema garanta as regras que estão descritas em 5.1.2 relativo a aulas e aulas extra. Em termos de user interface para cada um desses casos de uso não existem requisitos específicos. Nesse aspeto de "user experience" devem seguir boas práticas. Mas isso já faz parte do desenho da solução. "O cliente não percebe muito disso :-)" |  |  |  | DONE |  |  | DONE
55 | Thursday, 20 de April de 2023 às 13:46 | Class duration and time From what time to what time can a class be scheduled (eg: can the course have a class at 3AM?). And what’s the minimum and maximum duration for a class? i supose we can’t have 43m classes? | (n respondeu)
56 | Thursday, 20 de April de 2023 às 15:38 | Manager Data Um manager pode conter dados como "Birth Date" e "Tax Payer Number", assim como o Teacher e o Student? | Para o que se pretende actualmente essa informação não é relevante/útil para os managers. Mas, como cliente, não me parece que seja grave se puder ser registada também para esses utilizadores. |  |  | DONE
57 | Friday, 21 de April de 2023 às 11:36 | estado do curso US 1002 Na US 1002 temos de abrir e fechar as inscrições num curso, mas estas ações só são possíveis tendo em conta o estado do curso. Como fazemos para alterar o estado, ou seja, ao fazer as inscrições num curso passa automaticamente do estado event open (->state open) para o estado event open enrollments (-> state enroll) quando alguém é inscrito no curso ou é no intuito de dar a opção de trucar de estado. Para poder chegar ao estado de abertura das inscrições o curso tem de estar no estado event open (->state open), mas como o curso é criado no estado event create (-> state close) não podemos iniciar as inscrições sem que o curso tenha mudado de estado. Com isto quero perguntar se temos de ter também as opções de mudar de estado um curso sem ser referente as inscrições. A segunda opção é na US 1001 quando um curso é criado ele por defeito vai estar no estado event create (-> state close) ou passa logo para o estado event open (->state open) é o estado event create só é aplicado durante a criação do curso. | Por favor siga o processo que indiquei em https://moodle.isep.ipp.pt/mod/forum/discuss.php?d=22571#p28540 antes de colocar a questão.
58 | Friday, 21 de April de 2023 às 14:36 | US1004 - As Manager, I want to open and close courses É nos dito que uma course fechada não pode ter atividade.Tendo em conta isto: 1-Uma course que tenha aulas/exame marcados pode ser fechada? 2-Caso seja possível, o que acontecerá com estas atividades? Devemos cancelá-las? | Por favor siga o processo que indiquei em https://moodle.isep.ipp.pt/mod/forum/discuss.php?d=22571#p28540 antes de colocar a questão.
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174
175
176
177
178
179
180
181
182
183
184
185
186
187
188
189
190
191
192
193
194
195
196
197
198
199
200
201
202
203
204
205
206
207
208
209
210
211
212
213
214
215
216
217
218
219
220
221
222
223
224
225
226
227
228
229
230
231
232
233
234
235
236
237
238
239
240
241
242
243
244
245
246
247
248
249
250
251
252
253
254
255
256
257
258
259
260
261
262
263
Note on E6: João Nuno Leitão: Com given name é tipo um user name como Leitxuga?
Note on D24: João Nuno Leitão: This information is inputed by the administrator

## USs
LAPR4 - Client
User Stories Organization |  |  | US TYPES:
|  |  | FUNCTIONAL REQUIREMENTS |  |  |  |  | NON-FUNC | ACTORS
NUM | TITLE | DESCTIPTION | USER | COURSES | EXAMS | BOARDS | MEETINGS | Non-Functional Requirement | Managers / Administrators | Teachers | Students | System | Classes | Extra Classes | Students Enrollment | Teacher in charge | Evaluation | _ | _
FRB01 | Create Board | A user creates a board | x |  |  | x
FRB02 | Share Board | A user shares a board it owns with other users | x |  |  | x
FRB03 | View Board | The system should display, in "real-time", the shared boards available to the user in a HTML page |  |  |  | x | [5 empty] | x
FRB04 | Create Post-it | A user creates a post-it on a board | x |  |  | x
FRB05 | Change Post-it | A user changes a post-i | x |  |  | x
FRB06 | Undo Post-it Change | A user undo the last change in a post-i | x |  |  | x
FRB07 | View Board History | A user views a history of updates in a board | x |  |  | x
FRB08 | Archive Board | The owner of a board can archive the board | x |  |  | x
FRC01 | Create Course | Different editions of a course are to be considered different courses (e.g., Intro-Math-Sem01, Intro-Math-Sem02). Only managers are able to execute this functionality |  | x |  |  |  |  | x
FRC02 | Open/Close Enrollments in Course | Only managers are able to execute this functionality. |  | x |  |  |  |  | x
FRC03 | Open/Close Course | Only managers are able to execute this functionality. |  | x |  |  |  |  | x
FRC04 | Set Course Teachers | Each course may have several teachers and must have only one Teacher in Charge. Only managers are able to execute this functionality. |  | x |  |  |  |  | x
FRC05 | List Courses | All users are able to execute this functionality. |  | x |  |  |  |  | x | x | x
FRC06 | Bulk Enroll Students in Course | This can be made by importing a csv file with students. Only managers are able to execute this functionality |  | x |  |  |  |  | x
FRC07 | Request Enrollment in Course | The student requests to be enrolled in a course |  | x | [6 empty] | x
FRC08 | Approve/Reject Enlistment in Course | A manager approves or rejects a students’ application to a course. |  | x |  |  |  |  | x
FRC09 | Schedule of Class | A teacher schedule a class (always a recurring class, happens every week). System must check if the Teacher is available for the class period |  | x | [5 empty] | x |  | x
FRC10 | Schedule of Extra Class | A teacher schedule an extraordinary class. An extra class is a one occurrence only and it has a specific group of participants (a subset of the class students) | [7 empty] | x |  | (??? System must check if the Teacher is available for the class period ???) | x | x
FRC11 | Update Schedule of Class | A teacher changes the time of a specific class (only changes a specic occurrence of a recurring class). | [7 empty] | x |  |  | x
FRE01 | Create Exam | A Teacher creates a new exam. This includes the specification of the exam (i.e., its structure, in accordance with a grammar for exams that is used to validate the specification of the exam (????)) |  |  | x |  |  |  |  | x
FRE02 | List Exams | The system displays to a student his/her future exams. |  |  | x | [5 empty] | x | x
FRE03 | List Course Exams | The system displays to a teacher of a course all the exams of the course |  |  | x |  |  |  |  | x
FRE04 | Take Exam | A Student takes an exam and answer its questions. At the end of the exam, the system should display the feedback and result (i.e., grade) of the exam. The feedback and grade of the exam should be automatically calculated by a parser based on the grammar dened for exams structure. |  |  | x | [5 empty] | x | x
FRE05 | List Grades | The system displays to a students his/her grades |  |  | x | [5 empty] | x | x
FRE06 | List Course Grades | The system displays the grades of a class (to a teacher of that course) |  |  | x |  |  |  |  | x |  | x
FRM01 | Schedule a Meeting | A user schedules a meeting. The system must check if all participants are available and send invitations to participants. | x |  |  |  | x
FRM02 | Cancel Meeting | A user cancels a meeting that he owns | x |  |  |  | x
FRM03 | Accept/Reject Meeting | A user accepts or rejects an invitation to a meeting | x |  |  |  | x
FRM04 | List Participants | The system displays the lists of participants in a meeting and the response status (accept or reject meeting) |  |  |  |  | x |  |  |  |  | x
FRU01 | Management of Users | Create, disable/enable, and list users of the system (Teachers and Students, as well as Managers). It should be only available to managers of the system. | x | [5 empty] | x
General Description | ALL | All users can create and use boards as well as meetings. | x |  |  | x | x
General Description | Classes and Meeting | Classes and meetings are events that happen in some time and have a duration. However there is no concept of location related to classes and meetings. They do not take place in a specic location and "nothing" happens at the time of the event |  |  |  |  | x | [5 empty] | x
General Description | Classes and Meetings | Classes and meetings have participants |  |  |  |  | x | [5 empty] | x
General Description | Exams | For the moment the goal is to support online exams that can be automatically graded. |  |  | x
General Description | Exams
General Description | Exams | The system must also support the automatic production of feedback and grading for the answers given by students when they take the exam. Usually this is done at the end of the exam |  |  | x | [5 empty] | x | x
General Description | Exams | Analyze the problem and design a solution that supports the two goals: - validate the structure of the exam - evaluate the answers of each exam (giving feedback and calculating the grade) |  |  | x
General Description | Exam Organization | Each exam specication must include a set of components or sections: - Title: The title of the exam specification. - Header: This component must include global settings, such as the type of feedback (none, on-submission, after-closing) and the type of grade (none, on-submission, after closing). It may also contain a textual description to appear at the beginning of the exam **VER IMAGEM ENUNCIADO** - Sequence of Sections: After the header, the exam is composed of sequence of one or more sections. Each section is a group of questions. Each section may contain a textual description to appear at the beginning of the group of questions. The type of questions that can be used in the sections is described next
General Description | Question Types
General Description | Exams
General Description | Exams
General Description | Exams
General Description | Exams
General Description | Exams
General Description | Exams
General Description | General Description
General Description | General Description
General Description | General Description
General Description | General Description
General Description | Students | Students take exams and can view the results of their exams |  |  | x | [5 empty] | x
General Description | Teachers | Teachers can create exams. |  |  | x |  |  |  |  | x
General Description | Teachers | An exam is related to a specific course. |  | x | x
General Description | Teachers | An exam has: - a unique title - a small description. Exams have also: - a open date (the time when students can start to take the exam) - a close date (the deadline for students to submit the exam.) |  |  | x
General Description | Managers | - All users should be identified in the system by their email - Each user should also provide its full name and short name - In order to be authenticated by the system the users must also provide a password. | x
General Description | Course | A course is characterized by: - its title - a unique code (inputed by the administrator, e.g., "JAVA-1".) |  | x
General Description | Course | The usual work ow related to the course can be illustrated as follows: event create (-> state close) -> event open (->state open) -> event open enrollments (-> state enroll) -> event close enrollments (-> state in progress) -> event close (-> state closed) |  | x
General Description | Managers | Managers (they can be also named as Administrators) manage all the users of the system as well as courses and students enrollment. | x | x |  |  |  |  | x | [5 empty] | x
General Description | Managers | Each course should have a unique identifier (automatically generated) and a unique name. |  | x
General Description | Managers | A course may be open or closed. A closed course can not have any activity |  | x
General Description | Managers | Each course must have a teacher in charge, but may also have other teachers. |  | x | [5 empty] | x | [5 empty] | x
General Description | Managers | Courses are not divided into sections (i.e., "turmas"). |  | x
General Description | Managers | Students of the course participate in all classes of the course |  | x | [6 empty] | x |  | x
General Description | Managers | Courses may have a minimum and a maximum number of enrolled students. This may limit the possibility of opening (i.e. starting) courses that do not satisfy the limits |  | x | [10 empty] | x
General Description | Managers | A course has also a small textual descriptions of its contents. |  | x
General Description | Students | Students enroll in courses |  | x | [6 empty] | x
General Description | Students | A student is characterized by: - his/her name - date of birth - tax payer number - mechanographic number (assigned automatically by the system based on the year of registration and a sequential number, e.g., "202300001".) | [8 empty] | x
General Description | Teachers | Teachers are responsible for scheduling classes for their courses. A class is always a recurring weekly event |  | x | [5 empty] | x |  |  | x
General Description | Teachers | A class must have a unique title, a date and a duration | [10 empty] | x
General Description | Teachers | It should be impossible to schedule classes that are coincident with other classes of the same course. | [9 empty] | x | x
General Description | Teachers | The system should also warn if one of the participants in the class (either a teacher or a student) has other classes at the same time. | [7 empty] | x | x | x | x
General Description | Teachers | Teachers can schedule extra classes | [7 empty] | x |  |  | x | x
General Description | Teachers | A Teacher is characterized by: - his/her name - date of birth - tax payer number - acronym inputed by the administrator (e.g., "AALB") | [6 empty] | X | X
NFR09 | Exam Language | The support for exams (its design, feedback and grading) must follow specic technical requirements, specied in LPROG. The ANTLR tool should be used (https://www.antlr.org/). |  |  | x
NFR10 | Shared Board Architecture | This functional part of the system has very specic technical requirements. It must follow a client-server architecture, where a client application is used to access the shared boards that should be implemented in a server. Communications between these two components must follow specific protocol described in a document from RCOMP ("Application Protocol"). Also, the client application can not access the relational database, it can only access the server application. The client app should implement an HTTP server to be able to generate the "views" of the boards. This should be done automatically, without the intervention of the users (i.e., without reload of the web page) by using AJAX |  |  |  | x
NFR11 | Explore Shared Board Synchronization | This functional part of the system has very specic technical requirements, particularly some concerns about synchronization problems. In fact, several clients will try to concurrently update boards. As such, to explore and study this concurrency scenario a "model" of a solution must be implemented and evaluated exceptionally using the C programming language, and using processes and semaphores. Specic requirements will be provided in SCOMP. |  |  |  | x
NFR13 | Design and Implement Shared Board Synchronization | This functional part… As such, the solution design and implementation must be based on threads, D69condition variables and mutexes. Specic requirements will be provided in SCOMP. |  |  |  | x
NFR14 | Deployment | The solution should be deployed using several network nodes. It is expected that, at least, the relational database server and the shared board server be deployed in nodes di erent from localhost, preferably in the cloud |  |  |  | x
System Description | Shared Boards | The project aims to implement the concept of shared board, as a board that can be used to share and organize ideas and information |  |  |  | x
System Description | Shared Boards | s s s s s s s s s s |  |  |  | x
System Description | Automated Exams | The plataform should support a fully automated approach for exams and evaluation. |  |  | x | [11 empty] | x
System Description | Automated Exams | Teachers should be able to design exams using a simple and intuitive language |  |  | x |  |  |  |  | x
System Description | Automated Exams | Students should be able to take these exams and automatically have feedback and resulting grades after submitting them |  |  | x | [5 empty] | x
System Description | Automated Exams | The platform should also present dashboards about exam results both to students and teachers. |  |  | x |  |  |  |  | x | x
System Description
System Description
System Description
General Description
Note on D21: João Nuno Leitão: Only a manager can do this?
Note on D23: João Nuno Leitão: (??? System must check if the Teacher is available for the class period ???)
Note on D26: João Nuno Leitão: The sudent asks the system for future exams
Note on D28: João Nuno Leitão: Tem mais partes relacionadas/dependentes: - UC do studante fazer um exame em si - Exame estar disponível para o estudante, na plataforma. - UC do prof criar o exame.
Note on D34: João Nuno Leitão: Is this displayed when a user askes to or is it independent of a user interaction and also is it displayed to all users?

## Q_para_cliente
Teacher schedules classes In the documment we can read: "Teachers are responsible for scheduling classes for their courses" and also "Each course must have a teacher in charge". Our question is: Can any teacher schedule classes for the courses he/she is in or only the teacher in charge can schedule classes for the course she is in charge? If only the teacher in charge for that course can shedule classes does that also mean that only he/she can shedule extra classes? In the doccument we can also read: "Teachers can create exams." which made us question the same responsability problem. In addition, could you clarify what responsabilities the teacher in charge has that a normal teacher of a course hasn't, in the system? And also, if you find it relevant, give some pratical examples of what the teacher in charge will do in the system? Regards, Group 46. | Teacher schedules classes Can a teacher schedule a class for a closed course? (a meu ber faz sentido que sim)
Extra classes When will a teacher need to schedule an extra class? Only when he/she misses a class and has to give that class in another time that is not the normal recurring class schedule? taking this to account: "FRC11 - Update Schedule of Class A teacher changes the time of a specific class (only changes a specic occurrence of a recurring class)" There is no need to schedule an extra class in the terms I puted before An Extra class then is a special class for students in need?
a teacher in charge pode não ser um course teacher? Existe alguma d
Quais são as diferenças entre teacher in charge e course teacher
Quais são as responsabilidades que são do teacher in charge e não são do teacher
What are the common responsabilities between them